## Timeline
Screens | Front-End UI Expected Time(hrs) | Front-End API Linking Expected Time(hrs) | Back-End API Expected Time(hrs)
Welcome page | 1 | 1
Login | 2 | 2
Register | 3 | 3
Dashboard | 1 | 1
Setup
Numbering | 1
Game Setup
Play
Display
Game screen
Verify
Bingo 90 Tickets
Approve Users
Reports
Game details
Help | 0.5 | 0.5
Feedback | 1 | 1

## FE task status
Date | Task Type | From | To | Total Hours Spent | Task Detail | Notes | Status
2021-07-21 | Designing | 15:00 | 16:15 | 1:15 | Numbering |  | In-Progress
2021-07-21 | Designing | 15:00 | 16:15 | 1:15 | Dashboard | UI completed | Completed
2021-07-21 | Designing | 14:00 | 15:00 | 1:00 | Register | UI completed and linked to the link | Completed
2021-07-21 | Designing | 13:30 | 14:00 | 0:30 | Login | UI completed and linked to the link | Completed
2021-07-21 | Designing | 12:30 | 13:30 | 1:00 | Welcome page | UI completed | Completed

## Sheet2
Development | Completed
Designing | Learnt
RND | Kept Pending
Learning | In-Progress
Other